**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared: 17/04/2025 |

Report Prepared By Team Members: Pornpajee Sunkkadithee

Parisa Mohammadkarimi

Miguel Angel

Mehmet Ali Kaba

Employer/Organization (if applicable) :

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | Rose- Flower Delivery Mobile App | |
| T38 | |
| Start Date: Feb1**, 2025** | End Date: March27**, 2025** |
| Green (Good) | |

Summary

|  |
| --- |
| **Project Status Summary** |
| The project is progressing as planned, with adjustments made to the timeline due to delays in November and December. The team has rescheduled key development tasks for January and February to accommodate these delays while ensuring that all critical milestones will be met by the March 27, 2025, deadline. Despite the delays, the overall scope and objectives of the project remain achievable with the revised timeline. The focus in the upcoming period is to enhance the customer and driver platforms, integrate necessary third-party services, and continuously evaluate the design to ensure the project meets user expectations and is delivered on time. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| **Initial Planning and Coordination**: Completed team coordination and planning as scheduled. | **Payment System Integration**: Integration of the third-party payment solution was delayed. |
| **Scope and Objective Definition**: The project's scope, objectives, and overall structure were defined and approved. | **Testing and Quality Assurance**: Testing and quality assurance activities did not begin as planned due to resource constraints. |
| **Milestone and Deliverable Outline**: Milestones and deliverables for the project were outlined, ensuring clarity of expectations. | **Order History Feature**: The development of the comprehensive order history feature was pushed to the next phase due to prioritization of core platform functionalities. |
| **Team Task Allocation**: The team was organized, with clear assignments made for the development and integration tasks. | **Profile Settings Refine**: Refining the profile section with advanced settings was delayed due to higher priority tasks, such as navigation and payment system integration. |

Upcoming Objectives for **Mar 08, 2025 to Mar 27, 2025**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To  <name/s> | Duration  <days> | Date |
| Complete Customer Platform Enhancements | Pornpajee sunkkadithee | 5 days | Mar 08, 2025 - Mar 12, 2025 |
| Integrate Payment System | Parisa Mohammadkarimi | 7 days | Mar 08, 2025 - Mar 12, 2025 |
| Finalize Order History Feature Development | Mehmet Ali Kaba | 5 days | Mar 10, 2025 - Mar 14, 2025 |
| Refine Driver Profile Settings | Mehmet Ali Kaba | 4 days | Mar 15, 2025 - Mar 18, 2025 |
| Improve Navigation Features for Driver App | Miguel Angel Gutierrez | 5 days | Mar 19, 2025 - Mar 23, 2025 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Complete Payment System Integration | | Parisa Mohammadkarimi | Mar 14, 2025 |
| Launch Enhanced Customer Interface | | Pornpajee sunkkadithee | Mar 17, 2025 |
| Integrate Social Login Feature | | Mehmet Ali Kaba | Mar 19, 2025 |
| Final Testing and QA | | Mehmet Ali Kaba | Mar 23, 2025 |
| Prepare for Final Deployment | | Miguel Angel Gutierrez | Mar 26, 2025 |

Managing Issues and Risk (for current reporting period and next period)

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Delay in Payment System Integration | Prioritize third-party integration tasks and allocate additional resources for quicker implementation. | Mar 14, 2025 |
| Incomplete Order History Feature Development | Adjust development priorities to complete this feature by the end of the next period. | Mar 14, 2025 |
| Testing Delays | Reallocate resources to focus on testing, with the goal of beginning full testing by Mar 15, 2025. | Mar 15, 2025 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Integration Delays (Payment System, Social Login) | High | High | Schedule regular check-ins with integration teams, ensure contingency plans are in place. |
| latform Compatibility Issues | Medium | Medium | Conduct early testing on various devices and operating systems to identify issues before final deployment. |
| Resource Allocation and Team Availability | High | Medium | Monitor team workload closely, adjust deadlines or hire additional resources if necessary. |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “W25\_T<team number>\_ProjectReport2”.

For e.g., W25\_T99\_ProjectReport2

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, Mar 09, 2025 (11:59 p.m.)**